## GANTT Chart
Time (weeks):
[6 empty] | Seminar 1 | [6 empty] | Seminar 2 |  | Research Paper Due
Tasks: | Wk. 1 (17 Feb) | Wk. 2 (24 Feb) | Wk. 3 (3 Mar) | Wk. 4 (10 Mar) | Wk. 5 (17 Mar) | Wk. 6 (24 Mar) | StuVac (31 Mar) | Wk. 7 (7 Apr) | Wk. 8 (14 Apr) | Wk. 9 (21 Apr) | Wk. 10 (28 Apr) | Wk. 11 (5 May) | Wk. 12 (12 May) | Wk. 13 (19 May) | Wk. 14 (ending 31 May)
1. Understand Stage
1.1. Form project team and assign roles
1.2. Review project brief and assessment requirements
1.3. Define project objectives and measurable success criteria
1.4. Conduct literature review on fuzzy logic control systems
1.5. Conduct literature review on Ball and Beam dynamic modelling
1.6. Analyse existing fuzzy control designs for ball and beam systems
1.7. Internal team agreement on scope, tools (MATLAB/Python/Arduino), and responsibilities
2. System Design
2.1. Initial Concepts based on Project Requirements
2.2. Review Critical Requirements
2.3. System block diagram completed
3. Fuzzy Logic Development
3.1.
3.2.
3.3.
4. Simulation and Integration
4.1. Test Prototype with Simulation
4.2. Prove model will function (simulated)
4.2.1. If model is not viable with simulation, return to 3.3
4.3.
5. Testing and Validation Stage
5.1.
5.2.
5.3.
5.4.
6. Seminar Preparation
6.1 Seminar 1
6.2 Seminar 2
5. Research Paper
5.1. Draft Introduction and Problem Statement
5.2 Write Literature Review section
5.3 Document System Modelling and Controller Design
5.4 Document Implementation details (simulation / hardware)
5.5 ?
5.6 ?
5.7 ?
5.8 Final formatting and submission before 31 May 2026